## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)
TEAM MEMBERS	Team Mamber Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Team_Status
TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Eclipse	Preparation	Elliot	4		Planned	Using IDEs can make our job easier
Role preferences	Coordination	Matt	0.5	0.3	Done		0.2	66.6666666667
SVN Repository setup	Preparation	John	1	1.5	Ongoing		-0.5	33.3333333333
Discuss bug report software	Preparation	Seth	1.5	0	Delayed	This is critical to project success	1.5
Develop questions for requirements elicitation	Documentation	Sean	5		Planned	Make sure scoping questions are included
Get account and configure website	Preparation	Elliot	1.5	1	Done		0.5	50
Research existing technology	Preparation	Matt	2	1.5	Ongoing		0.5	33.3333333333
Project synopsis writeup	Documentation	Elliot	2		Planned
Identify role owners	Preparation	Matt	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	John	1	2	Done		-1	50
Status tracker	Documentation	Seth	1		Planned
Week 7 (sept 12 - sept 18)

Week 8 (sept 19 - sept 25)

Week 9

Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	7
PROJECT NAME	Academic Early Alert System
PROJECT MENTOR	Dr. Raghu Reddy

Actvities	Aditya Jain		Juhi Tandon		Raveesh Motlani		Karan Aggarwal		Team Member Name 5		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Web2py	3	4	4	5	5	6	8	15			20	30
Role preferences	0.2	0.25	0.25	0.25	0.2	0.2	0.2	0.2			0.85	0.9
SVN Repository setup	0.1	0.25	NA	NA	NA	NA					#VALUE!	#VALUE!
Discuss bug report software	NA	NA	NA	NA	NA	NA	NA	NA			#VALUE!	#VALUE!
Develop questions for requirements elicitation	1	2	1	2	1	1.5	1	1.5			4	7
Get account and configure website	0.1	0.1	0.1	0.1	0.1	0.1	0.1	0.1			0.4	0.4
Research existing technology	1	1.5	1.5	2	2	1	2	1.5			6.5	6
Project synopsis writeup	1	2	1	2	1	2	1	2			4	8
Identify role owners	0.5	1	0.5	1	0.5	0.5	0.5	0.5			2	3
Team Meeting	2	3	2	3	2	3	2	3			8	12
Status tracker	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Week 7 (sept 12 - sept 18)
SRS Documentation (Initial Draft)	2	2	3	3	2	2	0	0			7	7
Team Meeting	0.5	0.75	0.5	0.75	0.5	0.75	0.5	0.75			2	3
Meeting with mentor	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25			1	1
Draft Mockups (in rough)	0	0	0	0	0.2	0.5	0	0			0.4	0.6
Week 8 (sept 19 - sept 25)
SRS Documentation (Final)	5	7	6	8	5	7	3	3			19	25
Team Meeting	5	6	5	6	4	6	4	6			18	24
Draft Mockups (on paper)	0.2	0.3	0.2	0.3	0	0	0	0
Meeting with mentor	0.5	0.6	0.5	0.6	0.5	0.6	0.5	0.6			2	2.4
Status Tracker	0.25	0.25	0.25	0.25	0.25	0.25	0.25	0.25
Learn DB Management	4	4.5	4	5	1	1	1	2
Week 9						0	0
Design DB of the system	4	3	4	3	3	2	3	2			14	10
Implemented Database Design	4	3	4	3	4	3	4	3
Basic Implementation	5	6	5	6	5	6	5	6			20	24
Full Implementation for R1	2	3	2	3	4	3	3	3
Week 10						0	0
Prepared Design Document	2	3	2	3	2	3	2	3			8	12
Test Plan creation	1	1.5	1	1.5	1	1.5	1	1.5
Module Testing	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Integrated Testing	1	1	1	1	1	1	1	1
Week 11						0	0
Presentation document creation	1	1	1	1	1	1	1	1
Presentation preparation	1	1	1	1	1	1	1	1			4	4
Presentation for R1	2	2	2	2	2	2	2	2			8	8
Week 12						0	0
Planning for R2	1	1.5	0.5	1	0.5	1	0.5	1			2.5	4.5
Week 13						0	0
Design of UI Mockup	1	2	1	2	1	2	1	2			4	8
Meeting with the Client	0.5	0.25	0.5	0.25	0.5	0.25	0.5	0.25			2	1
Learnt Bootstrap	2	3	1	2	3	2	3	2			9	9
0						0	0
Week 14						0	0
UI changes on homepage	2	2	2	1	2	2	2	1			8	6
Default of roles	0.5	0.5	0.5	0.5	0.5	0.5	0.5				2	1.5
Learnt Bootstrap	3	4	3	4	3	3	3	3			12	14
Week 15						0	0
UI changes on all views	4	5	3	4	4	5	3	4
Learnt Ajax & Jquery	3	4	4	5	2	3	3	4			12	16
Testing	2	2	2	2	2	3	2	3			8	10
Week 16						0	0
Prepare for R2	2	2	2	2	2	2	2	2			8	8
Final UI changes	2	2	2	2	2	2	2	2			8	8
Security Signatures	1	1	1	1	1	1	1	1			4	4
Week 17						0	0
DEPLOY on college server	1.5	2	1.5	2	1.5	2	1.5	2			6	8
Cross Browser testing	1	2	1	2	2	3	1	2			5	9
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0